## ECI-LCO Matrix
ECI / LCO × Duckie — Scenario Matrix & Game Plan
As of June 30, 2026 ¦ Sources: #gx-duckie-integration-internal, #proj-duckie-avantstay, Duckie runs data
■ LIVE |  | ■ PARTIAL |  | ■ BLOCKED / NOT STARTED |  | ■ N/A FOR DUCKIE
Scenario | Type | ZD Tag(s) | Duckie Step 1 Detect & Classify | Duckie Step 2 Check Availability | Duckie Step 3 Action / Response | Duckie Step 4 VAS in Voyage | Duckie Step 5 Lock Update (IoT) | Current Status | Outstanding / Next Step
EARLY CHECK-IN (ECI)
ECI — Pre-booking inquiry (Guest asks if ECI is possible before booking) | ECI | reservation_inquiry____early_check_in_avantstay | ✅ Tag detected on ticket | — Not needed (informational only) | ✅ Duckie replies with general ECI policy and pricing | — Not applicable | — Not applicable | ✅ LIVE | None — working. Confirm message includes correct pricing ($X/hr or flat fee).
ECI — Post-booking request, advance notice (Guest requests ECI days/weeks before stay) | ECI | booked_guest____adding_vas_/_eci_/_lco_avantstay early_check-in_____request_avantstay | ✅ Tag detected on ticket | ⚠️ getEciAvailability tool exists but NOT connected to Duckie workspace (Desiree flagged 6/23) | ⚠️ Duckie cannot confirm availability — must hand to human or give generic response | 🔴 VAS creation in Voyage not automated — human must create manually (Ashrit asking Igo/Wanderson re: barrier on 6/30) | — Not needed for advance ECI | ⚠️ PARTIAL | 1. Connect getEciAvailability to Duckie workspace (Joel/Francisco) 2. Unblock VAS auto-creation in Voyage (Igo/Wanderson — what is the barrier?) 3. Once both live, Duckie can fully resolve this scenario end-to-end
ECI — Day-of request (urgent) (Guest requests ECI same morning of check-in) | ECI | booked_guest____adding_vas_/_eci_/_lco_avantstay early_check-in_____request_avantstay | ✅ Tag detected on ticket | 🔴 getEciAvailability not connected | ⚠️ Duckie replied with +40pp resolution improvement in last 7d — but likely informational responses only, not true resolution | 🔴 VAS not auto-created | 🔴 IoT lock auto-update unknown — Ashrit asked Matt Garza 6/30, no answer yet. If locks do NOT auto-update, this requires manual IoT action even after Duckie approves | ⚠️ PARTIAL | HIGHEST PRIORITY: 1. Confirm with Matt Garza: do locks auto-update when ECI applied day-of? (needed to know if full automation is possible) 2. Connect availability tool 3. Automate VAS creation 4. If locks need manual IoT — build Slack alert to IoT team as interim step
ECI — Market blocked (Port A, 30A, Lake Norman — ECI off through Oct 1) | ECI | booked_guest____adding_vas_/_eci_/_lco_avantstay early_check-in_____request_avantstay | ✅ Tag detected | — Should be skipped; market is blocked | 🔴 Does Duckie know these markets are blocked? No evidence it does — likely giving availability check or generic response instead of clean decline | — N/A (no VAS) | — N/A | 🔴 BLOCKED | Add market-aware logic to Duckie: if property in [Port A, 30A, Lake Norman], auto-respond 'ECI not available in this market through Oct 1' and mark resolved. Cameron posted this to #gx-team 6/30 — Duckie needs the same knowledge.
ECI — Re-confirmation (Guest confirms previously approved ECI time) | ECI | early_check-in_____re-confirming_avantstay | ✅ Tag detected (28 tickets in last 3mo) | — Not needed (already approved) | ✅ Duckie should be able to reply with confirmed ECI time from Voyage | — N/A | — N/A | ✅ LIVE | Verify Duckie is pulling confirmed ECI time from Voyage correctly and not giving a generic response.
ECI — Confirming standard check-in time (Guest asks what time check-in is) | ECI | early_check-in_____confirming_current_times_avantstay | ✅ Tag detected (17 tickets in last 3mo) | — N/A | ✅ Informational — Duckie replies with standard check-in time | — N/A | — N/A | ✅ LIVE | None — low volume, likely working.
ECI — Hotel properties (ECI/LCO at hotel-type properties, different workflow) | ECI | booked_guest____adding_vas_/_eci_/_lco_hotel_multi_clone reservation_inquiry____adding_vas_/_eci_/_lco_hotel_multi_clone | ✅ Tag detected | 🔴 Different availability system than STR | 🔴 Cameron noted 4/30: 'pending engineering support to go live' — unclear if this was ever shipped | 🔴 Hotel VAS workflow different from STR | — N/A (hotels handle differently) | 🔴 BLOCKED | Clarify with Igo/Francisco: was the hotel ECI workflow ever built? If not, scope and prioritize. Hotel properties may have different Voyage fields.
ECI — Same-day booking property (Properties like 'The Code' that accept same-day bookings) | ECI | reservation_inquiry____early_check_in_avantstay | ✅ Tag detected | 🔴 Bug: Duckie incorrectly told guest ECI not possible at The Code (same-day booking property) — filed in #zendesk-support 6/30 by Jaime Rodriguez | 🔴 Duckie applying standard ECI logic to a property that shouldn't have that restriction | — N/A until detection fixed | — N/A | 🔴 BLOCKED | Bug fix: add property-level flag for same-day booking properties so Duckie doesn't block ECI incorrectly. Needs property metadata from Voyage or a manual exception list.
LATE CHECK-OUT (LCO)
LCO — Pre-stay request (Guest requests LCO days/weeks before checkout) | LCO | late_check-out_____request_avantstay booked_guest____adding_vas_/_eci_/_lco_avantstay | ✅ Tag detected (225 tickets in last 3mo) | 🔴 getLcoAvailability exists but not connected to Duckie (Desiree flagged same issue as ECI availability, 6/23) | 🔴 Duckie cannot confirm LCO availability | 🔴 VAS not auto-created in Voyage | — N/A for LCO | 🔴 BLOCKED | Same blockers as ECI advance: 1. Connect getLcoAvailability tool to Duckie workspace 2. Automate VAS creation for LCO in Voyage LCO also needs SOP runbook connected (Desiree asked 6/23 — status unknown)
LCO — Day-of request (urgent) (Guest requests LCO morning of checkout) | LCO | late_check-out_____request_avantstay | ✅ Tag detected | 🔴 getLcoAvailability not connected | 🔴 Cannot confirm or deny automatically | 🔴 VAS not auto-created | — N/A | 🔴 BLOCKED | Same blockers as day-of ECI minus the lock question. Prioritize with ECI day-of workflow.
LCO — Market blocked (Port A, 30A, Lake Norman — LCO off through Oct 1) | LCO | late_check-out_____request_avantstay | ✅ Tag detected | — Should be skipped | 🔴 Duckie likely unaware of market block (same gap as ECI) | — N/A | — N/A | 🔴 BLOCKED | Same fix as ECI market block: add market-aware decline logic for Port A, 30A, Lake Norman through Oct 1.

## Game Plan
ECI / LCO Duckie — Game Plan (Priority Order)
# | Action Item | Owner | Dependency | Priority | Notes
1 | Confirm with Matt Garza: when ECI is applied day-of, do locks auto-update or does IoT have to manually intervene? | Ashrit → Matt Garza | None | 🔴 P0 | Determines if full day-of ECI automation is possible. If locks don't auto-update, need IoT Slack alert as interim solution.
2 | Connect getEciAvailability + getLcoAvailability tools to Duckie workspace | Joel / Francisco | None | 🔴 P0 | Desiree flagged 6/23 — tools exist but not wired up. This is the core blocker for Duckie resolving ECI/LCO end-to-end.
3 | Unblock VAS auto-creation in Voyage for ECI and LCO | Igo / Wanderson | getEciAvailability connected | 🔴 P0 | Ashrit asked 6/30 what the barrier is. Without this, Duckie can check availability but still can't complete the action.
4 | Add market-aware ECI/LCO logic: Port A, 30A, Lake Norman blocked through Oct 1 | Cameron / Duckie config | None | 🟠 P1 | Cameron posted to #gx-team 6/30. Duckie needs same knowledge or it will give wrong responses to guests in these markets.
5 | Fix same-day booking property bug (e.g. The Code) | Cameron / Igo | Property metadata from Voyage | 🟠 P1 | Bug filed 6/30 by Jaime Rodriguez in #zendesk-support. Duckie incorrectly blocking ECI at properties that allow same-day bookings.
6 | Clarify hotel ECI/LCO workflow — was it ever built? | Cameron → Francisco / Igo | None | 🟠 P1 | Cameron noted 4/30 this was pending engineering. Unknown if it shipped. Hotel workflow differs from STR.
7 | Connect ECI & LCO SOP runbooks to Duckie | Joel / Francisco → Desiree | Tools connected (item 2) | 🟡 P2 | Desiree asked 6/23. Ensures Duckie follows correct process logic once tools are live.
8 | Add Zendesk automation: duckie_resolved tag → set ticket status to Solved | Cameron / Igo | None | 🔴 P0 (separate) | This is the broader resolution issue — duckie_resolved tickets stay Open. Quick Zendesk trigger fix. Affects all scenarios, not just ECI/LCO.